## Template
Graph Type | Starting | Detail | End | Duration
left to right | Start |  | Build drive unit inventory | 0
| Start |  | Finalize Contract | 0
| Start |  | Film Assembly Process | 0
| Build drive unit inventory |  | Develop Work Package | 13
| Develop Work Package |  | Move Equipment | 1
| Finalize Contract |  | Move Equipment | 4
| Film Assembly Process |  | Send Crew to Tain New Supplier | 2
| Move Equipment |  | Test and Validate Equipment | 4
| Test and Validate Equipment |  | Site Visit with Project Team | 4
| Test and Validate Equipment |  | Qualify Drive Units | 4
| Test and Validate Equipment |  | Send Crew to Tain New Supplier | 4
| Send Crew to Tain New Supplier |  | End | 3
| Qualify Drive Units |  | End | 4
| Site Visit with Project Team |  | End | 1

## dropdown (hidden)
MM type | Graph Type
TB | top to bottom
TD | top-down/ same as top to bottom
BT | bottom to top
RL | right to left
LR | left to right