## Template
Graph Type | Starting | Detail | End | Duration
left to right | Start |  | get requirements | 0
| Start |  | confirm with client | 0
| get requirements |  | Build code base | 2
| confirm with client |  | Build code base | 1
| Build code base |  | Testing | 6
| Build code base |  | QA Testing | 6
| Testing |  | Review with Client | 5
| Testing |  | Review with PM | 5
| Review with Client |  | Push to Prod | 3
| Review with PM |  | Push to Prod | 2
| QA Testing |  | Push to Prod | 4
| Push to Prod |  | End | 1

## dropdown (hidden)
MM type | Graph Type
TB | top to bottom
TD | top-down/ same as top to bottom
BT | bottom to top
RL | right to left
LR | left to right